## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Login (User) | After login, edollar is not shown | Low | 1 | 26 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
2 | 1 | Bootstrap | Successful bootstrap doesn't show num-record-loaded in alphabetical order | High | 5
3 | 1 | Bootstrap | Blank field error messages don't show the names of the fields accordingly | High | 5
4 | 1 | Bootstrap | Bootstrap validation errors are not ordered according to filename (alphabetical) | High | 5
5 | 1 | Bootstrap | Bootstrap doesn't work on aws server | Critical | 10
6 | 2 | Bootstrap | Bootstrap throwing errors (Json 0009 & 0010) | High | 5 | 58 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
7 | 2 | Bootstrap | Bootstrap throws wrong errors with non-numeric edollar (1006-bootstrap) | High | 5
8 | 2 | Bootstrap | Bootstrap succeeded despite error in data (1506-boostrap) | High | 5
9 | 2 | Bootstrap | Bootstrap throws wrong errors when sections clashes (1512-bootstrap) | High | 5
10 | 2 | Bootstrap | Bootstrap throws wrong errors when exam clashes (1513-bootstrap) | High | 5
11 | 2 | Bootstrap | Bootstrap succeeded despite error in data (1514-bootstrap) | High | 5
12 | 2 | Bootstrap | Bootstrap throws wrong errors when course completed (1515-bootstrap) | High | 5
13 | 2 | Bootstrap | Bootstrap throws wrong errors when section limit reached (1516-bootstrap) | High | 5
14 | 2 | Start Round 2 (Admin) | Unable to start round 2 and continue testing due to database constraints | Critical | 10
15 | 2 | User Place Bid | User able to bid for duplicate sections of the same course | Low | 1
16 | 2 | User Place Bid | User able to bid for enrolled courses in round 2 | High | 5
17 | 2 | User Delete Bid | User able to delete bid outside of active rounds, unable to drop in bidded round | Low | 1
18 | 2 | User Drop Section | User unable to drop section druing active round | Low | 1
19 | 3 | Admin Update Bid | Wrong error message for section limit reached | Low | 1 | 66 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
20 | 3 | Admin Drop Section | Undefined index in drop-section.php | High | 5
21 | 3 | Admin dump bid | error message for invalid section is still shown even when course is invalid | Low | 1
22 | 3 | Admin dump bid | key "result" is not shown when bid information is retrieved | Low | 1
23 | 3 | Admin Update Bid | Error message returned due to calling function on array for updating a bid. | High | 5
24 | 3 | Admin Drop Section | Error message returned due to an unidentified index. | High | 5
25 | 3 | Admin Bid Dump | Error in BidDAO function 'retrieveByCourseSection' accepting too few arguments for bid object construction. | High | 5
26 | 3 | Admin Drop Section | Error message returned due to an unidentified index. | High | 5
27 | 3 | Admin Section Dump | Incorrect format for JSON output | Low | 1
28 | 3 | Admin Bid Dump | Bid minimum value not validated | High | 5
29 | 3 | Admin Bid Dump | incorrect 'out' output | High | 5
30 | 3 | Admin dump bid | Incorrect format for JSON output | Low | 1
31 | 3 | Admin dump bid | Section student not coded | High | 5
32 | 3 | User Place Bid | User is able to place bid in inactive round | High | 5
33 | 3 | User Place Bid | User is able to place bid for enrolled courses in round 2 | High | 5
34 | 3 | User Place Bid | Extra errors were shown when placing invalid bids | High | 5
35 | 3 | User Place Bid | User unable to place bid for other schools in round 2 | High | 5
36 | 3 | User Drop Section | User unable to drop section in active round | Low | 1
37 | 4 | User Place Bid | User can place bid in sections with no vacancies. Although bid fail. | Low | 1 | 78 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
38 | 4 | User Place Bid | Vacancy count after round 1 ended is not updated and shown in round 2. | High | 5
39 | 4 | Round 2 clearing logic | Error in bid status when bids placed > available vacancies, failed bids still show success status. | Critical | 10
40 | 4 | Round 2 clearing logic | Error shown in e-dollar balance of user after placing bids in round 2 | Low | 1
41 | 4 | Admin Stop Round/ Round 2 clearing logic | Error in the bidding results table after stop of round 2 bidding. | High | 5
42 | 4 | User Drop bid | Error message of "no such bid" is shown when user drops bid for a bid placed successfully in round 2. Drop Bid unsuccessful. | High | 5
43 | 4 | Bid-dump web service | DAO naming in bid-dump not consistent with file name, json unable to retrieve file | High | 5
44 | 4 | Student UI | Student bidding results not showing vacancy | High | 5
45 | 4 | Student UI | Student bidding results not showing minimum bid | High | 5
46 | 4 | Student UI | Student Timetable display bug | High | 5
47 | 4 | Student UI | Student able to see courses from other schools | High | 5
48 | 4 | Student UI | Student able to press add bid buttons when round is inactive | High | 5
49 | 4 | Admin UI | Admin UI display is not scalable | High | 5
50 | 4 | Admin UI | Admin UI buttons lead to 404 error | High | 5
51 | 4 | Admin UI | Admin current bid table search function not working | High | 5
52 | 4 | Admin UI | Admin current bid table showing wrong results for different rounds | High | 5

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Login (User) | After login, edollar is not shown | Resolved | 29/09/2019 | 30/09/2019 | WR & YF
2 | 1 | Bootstrap | Successful bootstrap doesn't show num-record-loaded in alphabetical order | Resolved | 29/09/2019 | 30/09/2019 | WR & YF
3 | 1 | Bootstrap | Blank field error messages don't show the names of the fields accordingly | Resolved | 29/09/2019 | 30/09/2019 | WR & YF
4 | 1 | Bootstrap | Bootstrap validation errors are not ordered according to filename (alphabetical) | Resolved | 30/09/2019 | 2019-01-10 | WR & YF
5 | 1 | Bootstrap | Bootstrap doesn't work on aws server | Resolved | 2019-01-10 | 2019-03-10 | Cliffen & XS
6 | 2 | Bootstrap | Bootstrap throwing errors (Json 0009 & 0010) | Resolved | 2019-07-10 | 2019-08-10 | Cliffen & XS
7 | 2 | Bootstrap | Bootstrap throws wrong errors with non-numeric edollar (1006-bootstrap) | Resolved | 14/10/2019 | 14/10/2019 | Cliffen & XS
8 | 2 | Bootstrap | Bootstrap succeeded despite error in data (1506-boostrap) | Resolved | 14/10/2019 | 14/10/2019 | Cliffen & XS
9 | 2 | Bootstrap | Bootstrap throws wrong errors when sections clashes (1512-bootstrap) | Resolved | 14/10/2019 | 14/10/2019 | Cliffen & XS
10 | 2 | Bootstrap | Bootstrap throws wrong errors when exam clashes (1513-bootstrap) | Resolved | 14/10/2019 | 14/10/2019 | Cliffen & XS
11 | 2 | Bootstrap | Bootstrap succeeded despite error in data (1514-bootstrap) | Resolved | 14/10/2019 | 14/10/2019 | Cliffen & XS
12 | 2 | Bootstrap | Bootstrap throws wrong errors when course completed (1515-bootstrap) | Resolved | 14/10/2019 | 14/10/2019 | Cliffen & XS
13 | 2 | Bootstrap | Bootstrap throws wrong errors when section limit reached (1516-bootstrap) | Resolved | 14/10/2019 | 14/10/2019 | Cliffen & XS
14 | 2 | Start Round 2 (Admin) | Unable to start round 2 and continue testing due to database constraints | Resolved | 14/10/2019 | 14/10/2019 | Cliffen & XS
15 | 2 | User Place Bid | User able to bid for duplicate sections of the same course | Resolved | 14/10/2019 | 15/10/2019 | Cliffen & XS
16 | 2 | User Place Bid | User able to bid for enrolled courses in round 2 | Resolved | 14/10/2019 | 15/10/2019 | Cliffen & XS
17 | 2 | User Delete Bid | User able to delete bid outside of active rounds, unable to drop in bidded round | Resolved | 14/10/2019 | 15/10/2019 | Cliffen & XS
18 | 2 | User Drop Section | User unable to drop section druing active round | Resolved | 14/10/2019 | 15/10/2019 | Cliffen & XS
19 | 3 | Admin Update Bid | Wrong error message for section limit reached | Resolved | 2019-10-25 | 2019-10-30 | Cliffen & XS
20 | 3 | Admin Drop Section | Undefined index in drop-section.php | Resolved | 2019-10-25 | 2019-10-30 | Cliffen & XS
21 | 3 | Admin dump bid | error message for invalid section is still shown even when course is invalid | Resolved | 2019-10-25 | 2019-10-30 | Cliffen & XS
22 | 3 | Admin dump bid | key "result" is not shown when bid information is retrieved | Resolved | 2019-10-25 | 2019-10-30 | Cliffen & XS
23 | 3 | Admin Update Bid | Error message returned due to calling function on array for updating a bid. | Resolved | 2019-10-30 | 2019-10-30 | Cliffen & XS
24 | 3 | Admin Drop Section | Error message returned due to an unidentified index. | Resolved | 2019-10-30 | 2019-10-30 | Cliffen & XS
25 | 3 | Admin Bid Dump | Error in BidDAO function 'retrieveByCourseSection' accepting too few arguments for bid object construction. | Resolved | 2019-10-30 | 2019-10-30 | Cliffen & XS
26 | 3 | Admin Drop Section | Error message returned due to an unidentified index. | Resolved | 2019-10-30 | 2019-10-30 | Cliffen & XS
27 | 3 | Admin Section Dump | Incorrect format for JSON output | Resolved | 2019-10-30 | 2019-10-30 | Cliffen & XS
28 | 3 | Admin Bid Dump | Bid minimum value not validated | Resolved | 2019-10-30 | 2019-10-30 | Cliffen & XS
29 | 3 | Admin Bid Dump | incorrect 'out' output | Resolved | 2019-10-30 | 2019-10-30 | Cliffen & XS
30 | 3 | Admin dump bid | Incorrect format for JSON output | Resolved | 2019-10-30 | 2019-10-30 | Cliffen & XS
31 | 3 | Admin dump bid | Section student not coded | Resolved | 2019-10-30 | 2019-10-30 | Cliffen & XS
32 | 3 | User Place Bid | User is able to place bid in inactive round | Resolved | 2019-10-30 | 2019-10-30 | WR & YF
33 | 3 | User Place Bid | User is able to place bid for enrolled courses in round 2 | Resolved | 2019-10-30 | 2019-10-30 | WR & YF
34 | 3 | User Place Bid | Extra errors were shown when placing invalid bids | Resolved | 2019-10-30 | 2019-10-30 | WR & YF
35 | 3 | User Place Bid | User unable to place bid for other schools in round 2 | Resolved | 2019-10-30 | 2019-10-30 | WR & YF
36 | 3 | User Drop Section | User unable to drop section in active round | Resolved | 2019-10-30 | 2019-10-30 | WR & YF
37 | 4 | User Place Bid | User can place bid in sections with no vacancies. Although bid fail. | Resolved | 2019-12-11 | 2019-12-11 | Cliffen & XS
38 | 4 | User Place Bid | Vacancy count after round 1 ended is not updated and shown in round 2. | Resolved | 2019-12-11 | 2019-12-11 | Cliffen & XS
39 | 4 | Round 2 clearing logic | Error in bid status when bids placed > available vacancies, failed bids still show success status. | Resolved | 2019-12-11 | 2019-12-11 | Cliffen & XS
40 | 4 | Round 2 clearing logic | Error shown in e-dollar balance of user after placing bids in round 2 | Resolved | 2019-12-11 | 2019-12-11 | Cliffen & XS
41 | 4 | Admin Stop Round/ Round 2 clearing logic | Error in the bidding results table after stop of round 2 bidding. | Resolved | 2019-12-11 | 2019-12-11 | Cliffen & XS
42 | 4 | User Drop bid | Error message of "no such bid" is shown when user drops bid for a bid placed successfully in round 2. Drop Bid unsuccessful. | Resolved | 15/11/2019 | 16/11/2019 | Cliffen & XS
43 | 4 | Bid-dump web service | DAO naming in bid-dump not consistent with file name, json unable to retrieve file | Resolved | 15/11/2019 | 16/11/2019 | Cliffen & XS
44 | 4 | Student UI | Student bidding results not showing vacancy | Resolved | 15/11/2019 | 16/11/2019 | WR & YF
45 | 4 | Student UI | Student bidding results not showing minimum bid | Resolved | 15/11/2020 | 16/11/2020 | WR & YF
46 | 4 | Student UI | Student Timetable display bug | Resolved | 15/11/2021 | 16/11/2021 | WR & YF
47 | 4 | Student UI | Student able to see courses from other schools | Resolved | 15/11/2022 | 16/11/2022 | WR & YF
48 | 4 | Student UI | Student able to press add bid buttons when round is inactive | Resolved | 15/11/2023 | 16/11/2023 | WR & YF
49 | 4 | Admin UI | Admin UI display is not scalable | Resolved | 15/11/2024 | 16/11/2024 | WR & YF
50 | 4 | Admin UI | Admin UI buttons lead to 404 error | Resolved | 15/11/2025 | 16/11/2025 | WR & YF
51 | 4 | Admin UI | Admin current bid table search function not working | Resolved | 15/11/2026 | 16/11/2026 | WR & YF
52 | 4 | Admin UI | Admin current bid table showing wrong results for different rounds | Resolved | 15/11/2027 | 16/11/2027 | WR & YF