## Week 5
Person | Question | Week: 16/9/2019 to 22/9/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Cliffen | What did you do yesterday? |  |  |  | Create schedule and tasks for the iteration | Create folders and files in git repository | Brainstorm on additional test cases | Not a working day
| What will you do today? |  |  |  | Create folders and files in git repository | Create additional test cases | Not a working day | Not a working day
| Do you have any obstacles? |  |  |  | No | No | No | No
Wen Rui | What did you do yesterday? |  |  |  | Read functionality requirements and revise php to prepare for bootstrapping | Bootstrap data into sql database | Completed log in page and bootstrap | Non-working day
| What will you work on today? |  |  |  | Code login page UI, try bootstrapping data into databse | Code login page UI, try json for test cases | Not a working day | Try more json test cases
| Do you have any obstacles? |  |  |  | No | No | No | No
Yi Fan | What did you do yesterday? |  |  |  | set goals to complete for the entire iteration. | work on bootstrap to set up the database | Completed log in page, bootstrap and validation of data | non working day
| What will you work on today? |  |  |  | work on bootstrap to set up the database | continue to work on validation of data | Not a working day | come up with testcases to debug
| Do you have any obstacles? |  |  |  | took quite long to familiarise with bootstrap | no | No | no
Xian Shuang | What did you do yesterday? |  |  |  | Discussion as a group, allocated tasks | create test cases | Worked on test cases | Non-working day
| What will you work on today? |  |  |  | Create test cases | create test cases | Non-working day | Non-working day
| Do you have any obstacles? |  |  |  | No | No | No | No

## Week 6
Person | Question | Week: 23/9/2019 to 29/9/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Cliffen | What did you do yesterday? | Non-working day. | Relook at schedule to make sure everything is on track | Non-working day | Create test cases for validation | Started on test cases for JSON checker | Continue working on JSON Checker | Conduct manual testing
| What will you do today? | Relook at schedule to make sure everything is on track | Non-working day | Create test cases for validation | Continue working on test cases | Continue working on JSON Checker | Conduct manual testing | Work on JSON test cases
| Do you have any obstacles? | No | No | No | No | No | No | No
Wen Rui | What did you do yesterday? | Non-working day. | Non-working day. | Non-working day | Code validation for csv | Validate bootstrap data | Code user login page | Non working day
| What will you work on today? | Non-working day. | Non-working Day | Code validation for csv | Validate bootstrap data | Code user login page | Non working day | Non working day
| Do you have any obstacles? | No | No | No | No | No | No | No
Yi Fan | What did you do yesterday? | Non-working day. | Non-working day. | Non-working day | Code validation for csv | Validate bootstrap data | Code user login page | Non working day
| What will you work on today? | Non-working day. | Non-working day | Code validation for csv | Validate bootstrap data | Code user login page | Non working day | Non working day
| Do you have any obstacles? | No | No | No | No | No | No | No
Xian Shuang | What did you do yesterday? | Non-working day. | Non-working day | Non-working day | Create test cases for validation | Work on test cases | Non working day | Do manual test cases for login and check
| What will you work on today? | Non-working day. | Non-working day | Create test cases for validation | Work on test cases | Non working day | Do manual test cases for login and check | Non working day
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 7
Person | Question | Week: 30/9/2019 to 6/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Cliffen | What did you do yesterday? | Work on JSON test cases | Test, update test log and bug log | Upload database to AWS and assist in preparation for presentation slides | PM review | Start on bootstrap validation coding | Finish bootstrap validation coding | Continue on bootstrap validation
| What will you do today? | Test, update test log and bug log | Upload database to AWS and assist in preparation for presentation slides | PM Review | Start on bootstrap validation coding | Finish bootstrap validation coding | Continue on bootstrap validation | Conduct testing for functions done so far
| Do you have any obstacles? | No | No | No | No | No | No | No
Wen Rui | What did you do yesterday? | Modify code to prepare for creating of json test cases, created some json test cases | Finish creating json testcases, testing and maybe debugging | debugging and prepare for pm review | PM review | Fix critical bug of bootstrap, adjust admin authenticate function to align with project requirements | Start on admin start stop dump functions, fix authentication | Code admin start & stop & dump functions. Fixed admin authentication. Changed login validations to use tokens
| What will you work on today? | Finish creating json testcases, testing and maybe debugging | debugging and prepare for pm review | PM Review | Fix critical bug of bootstrap, adjust admin authenticate function to align with project requirements | Start on admin start stop dump functions, fix authentication | Code admin start & stop & dump functions. Fixed admin authentication. Changed login validations to use tokens | Create test cases and testing
| Do you have any obstacles? | No | No | No | No | No | No | No
Yi Fan | What did you do yesterday? | Non working day | Json checker testcases and testing | Debug and Prepare for presentation slides | PM review | Change admin page according to PM review, fix critical bug for Bootstrap Importing | Start on admin start stop dump functions, fix authentication | continue with admin page functionalities
| What will you work on today? | Json checker testcases and testing | Debug and Prepare for presentation slides | PM Review | Change admin page according to PM review, fix critical bug for Bootstrap Importing | Start on admin start stop dump functions, fix authentication | continue with admin page functionalities | Create test cases and testing
| Do you have any obstacles? | No | No | No | No | No | No | No
Xian Shuang | What did you do yesterday? | Manual testing of login and bootstrap | Json checker testing | Prepare for presentation slides | PM review | Work on Bootstrap & Json validation | Continue on bootstrap validation | Continue on bootstrap validation
| What will you work on today? | Json checker testing | Prepare for presentation slides | PM Review | Work on Bootstrap & Json validation | Continue on bootstrap validation | Continue on bootstrap validation | Testing
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 8
Person | Question | Week: 7/10/2019 to 13/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Cliffen | What did you do yesterday? | Conduct testing for functions done so far | Test and debug | Continue with debugging | Start coding for user bidding functions | Code user drop bid and view results function, create manual testcases | Continue with user bidding functions and creating testcases | final touch-up on the code
| What will you do today? | Test and debug | Continue with debugging | Start coding for user bidding functions | Code user drop bid and view results function, create manual testcases | Continue with user bidding functions and creating testcases | final touch-up on the code | Finish creating testcases as a team
| Do you have any obstacles? | No | No | No | No | No | No | No
Wen Rui | What did you do yesterday? | Create test cases and testing | Testing | Non-working day | Code adjustments to sessions and start/stop functions | Update admin dump function, browser UI for manual testing, create test cases | Continue with creating testcases | final touch-up on the code
| What will you work on today? | Testing | Non-working day | Code adjustments to sessions and start/stop functions | Update admin dump function, browser UI for manual testing, create test cases | Continue with creating testcases | final touch-up on the code | Finish creating testcases as a team
| Do you have any obstacles? | No | No | No | No | No | No | No
Yi Fan | What did you do yesterday? | Create test cases and testing | Testing | Non-working day | Code adjustments to sessions and start/stop functions | Update admin dump function, browser UI for manual testing, create test cases | Continue with creating testcases | final touch-up on testcases
| What will you work on today? | Testing | Non-working day | Code adjustments to sessions and start/stop functions | Update admin dump function, browser UI for manual testing, create test cases | Continue with creating testcases | final touch-up on testcases | Finish creating testcases as a team
| Do you have any obstacles? | No | No | No | No | No | No | No
Xian Shuang | What did you do yesterday? | Conduct testing for functions done so far | Test and debug | Continue with debugging | Start coding for user bidding functions | Code user drop bid and view results function, create manual testcases | Continue with user bidding functions and creating testcases | final touch-up on the code
| What will you work on today? | Test and debug | Continue with debugging | Start coding for user bidding functions | Code user drop bid and view results function, create manual testcases | Continue with user bidding functions and creating testcases | final touch-up on the code | Finish creating testcases as a team
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 9
Person | Question | Week: 14/10/2019 to 20/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Cliffen | What did you do yesterday? | Finish creating testcases as a team | Testing, debugging and deployment to AWS | Continue with testing, debugging and deployment to AWS | Prepare for online review and upcoming iteration | planning for this iteration and planning test cases. | Create manual and json test cases | Continued to create manual and json test cases
| What will you do today? | Testing, debugging and deployment to AWS | Continue with testing, debugging and deployment to AWS | Prepare for online review and upcoming iteration | planning for this iteration and planning test cases. | Create manual and json test cases | Continue to create manual and json test cases | Code admin update bid/ delete bid/ drop section functions
| Do you have any obstacles? | No | No | No | No | No | No | No
Wen Rui | What did you do yesterday? | Finish creating testcases as a team | Testing, debugging and deployment to AWS | Continue with testing, debugging and deployment to AWS | Prepare for online review and upcoming iteration | planning for this iteration and planning test cases. | Create manual and json test cases | Continued to create manual and json test cases
| What will you work on today? | Testing, debugging and deployment | Continue with testing, debugging and deployment to AWS | Prepare for online review and upcoming iteration | planning for this iteration and planning test cases. | Create manual and json test cases | Continue to create manual and json test cases | Code admin dump functions
| Do you have any obstacles? | No | No | No | No | No | No | No
Yi Fan | What did you do yesterday? | Finish creating testcases as a team | Testing, debugging and deployment to AWS | Continue with testing, debugging and deployment to AWS | Prepare for online review and upcoming iteration | planning for this iteration and planning test cases. | Create manual and json test cases | Continued to create manual and json test cases
| What will you work on today? | Testing, debugging and deployment | Continue with testing, debugging and deployment to AWS | Prepare for online review and upcoming iteration | planning for this iteration and planning test cases. | Create manual and json test cases | Continue to create manual and json test cases | Code admin dump functions
| Do you have any obstacles? | No | No | No | No | No | No | No
Xian Shuang | What did you do yesterday? | Finish creating testcases as a team | Testing, debugging and deployment to AWS | Continue with testing, debugging and deployment to AWS | Prepare for online review and upcoming iteration | planning for this iteration and planning test cases. | Create manual and json test cases | Continued to create manual and json test cases
| What will you work on today? | Testing, debugging and deployment to AWS | Continue with testing, debugging and deployment to AWS | Prepare for online review and upcoming iteration | planning for this iteration and planning test cases. | Create manual and json test cases | Continue to create manual and json test cases | Code admin update bid/ delete bid/ drop section functions
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 10
Person | Question | Week: 21/10/2019 to 27/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Cliffen | What did you do yesterday? | Code admin update bid/ delete bid/ drop section functions | Complete Code admin update bid/ delete bid/ drop section functions | admin round 2 clear logic and update manual test cases | Non-working day | Code UI for admin functions | Non-working Day | Non-working Day
| What will you do today? | admin round 2 clear logic | admin round 2 clear logic | Testing and integration | Code UI | Non-working Day | Non-working Day | round 2 clearing logic and improve UI
| Do you have any obstacles? | No | No | No | No | No | No | No
Wen Rui | What did you do yesterday? | Code admin dump functions | Code admin dump functions | Work on admin dump functions and Improve User Interface | Complete dump functions and code UI | Code UI for student functions | Non-working Day | Non-working Day
| What will you work on today? | Work on admin dump functions and Improve User Interface | Work on admin dump functions and Improve User Interface | Testing and integration | Code UI | Non-working Day | Non-working Day | Non-working Day
| Do you have any obstacles? | No | No | No | No | No | No | No
Yi Fan | What did you do yesterday? | Code admin dump functions | Code admin dump functions | Work on admin dump functions and Improve User Interface | Complete dump functions and code UI | Code UI for student functions | Non-working Day | Non-working Day
| What will you work on today? | Work on admin dump functions and Improve User Interface | Work on admin dump functions and Improve User Interface | Testing and integration | Code UI | Non-working Day | Non-working Day | Non-working Day
| Do you have any obstacles? | No | No | No | No | No | No | No
Xian Shuang | What did you do yesterday? | Code admin update bid/ delete bid/ drop section functions | Code admin update bid/ delete bid/ drop section functions | admin round 2 clear logic and update manual test cases | Non-working day | Code UI for admin functions | Non-working Day | Non-working Day
| What will you work on today? | admin round 2 clear logic | admin round 2 clear logic | Testing and integration | Code UI | Non-working Day | Non-working Day | round 2 clearing logic and improve UI
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 11
Person | Question | Week: 28/10/2019 to 3/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Cliffen | What did you do yesterday? | round 2 clearing logic and improve UI | continue round 2 clearing logic and improve UI | testing and integration | Debugging and code fixes in preparation for UAT | Iter 4 planning | Planning of json testing | Create json test cases
| What will you do today? | continue round 2 clearing logic and improve UI | testing and integration | Deployment to AWS, debugging and UAT. | Iter 4 planning and test plan | Planning of json testing | Create json test cases | Create more json test cases
| Do you have any obstacles? | No | No | No | No | No | No | No
Wen Rui | What did you do yesterday? | Non-working Day | testing and integration | testing and integration | Testing and debugging for UAT | Team meeting for iter 4 scheduling | Check wiki to plan for json testing | Create json test cases
| What will you work on today? | testing and integration | testing and integration | Regression testing, debugging and UAT | Team meeting for iter 4 scheduling | Check wiki to plan for json testing | Create json test cases | Create json test cases for iter 4
| Do you have any obstacles? | No | No | No | No | No | No | No
Yi Fan | What did you do yesterday? | Non-working Day | testing and integration | testing and integration | Testing functions and UAT | Meeting for iter 4 planning | Check wiki and plan for manual testing | Create manual test cases
| What will you work on today? | testing and integration | testing and integration | Regression testing, debugging and UAT | Meeting for iter 4 planning | Check wiki and plan for manual testing | Create manual test cases | Create manual test cases
| Do you have any obstacles? | No | No | No | No | No | No | No
Xian Shuang | What did you do yesterday? | round 2 clearing logic and improve UI | continue round 2 clearing logic and improve UI | testing and integration | Testing and prepare UAT | Team meeting to plan for iter 4 | Manual testing planning | Create manual test cases
| What will you work on today? | continue round 2 clearing logic and improve UI | testing and integration | Deployment to AWS, debugging and UAT. | Team meeting to plan for iter 4 | Manual testing planning | Create manual test cases | Create manual test cases
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 12
Person | Question | Week: 4/11/2019 to 10/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Cliffen | What did you do yesterday? | Non-working day | Create more json test cases | Create json test cases based on UAT | Team meeting and fiish creating json test cases | Debug webservices based on UAT results | Debug webservices based on UAT results | Debug webservices
| What will you do today? | Create more json test cases | Create json test cases based on UAT | Team meeting and finish creating json test cases | Debug webservices based on UAT | Debug webservices based on UAT results | Debug webservices | Code bid status web service
| Do you have any obstacles? | No | No | No | No | No | No | No
Wen Rui | What did you do yesterday? | Non-working day | Create more json test cases | Create json test cases | Team meeting and finish creating json test cases | Debug UI based on UAT | Debug UI based on UAT results | Debug UI based on UAT results
| What will you work on today? | Create more json test cases | Create json test cases | Team meeting and finish creating json test cases | Debug UI based on UAT | Debug UI based on UAT results | Debug UI based on UAT results | Non-working day
| Do you have any obstacles? | No | No | No | No | Some CSS issues from yesterday | No | No
Yi Fan | What did you do yesterday? | Create more manual test cases | Non-working day | Create manual test cases | Meeting & finish manual test cases | Debug UI based on UAT | Debug UI based on UAT | Debug UI based on UAT
| What will you work on today? | Non-working day | Create manual test cases | Meeting & finish manual test cases | Debug UI based on UAT | Debug UI based on UAT | Debug UI based on UAT | Non-working day
| Do you have any obstacles? | No | No | No | No | CSS grid problems | No | No
Xian Shuang | What did you do yesterday? | Create more manual test cases | Non-working day | Create manual test cases | Finish creating manual test cases | Debug webservices based on UAT | Debug webservices | Debug web services
| What will you work on today? | Non-working day | Create manual test cases | Finish creating manual test cases | Debug webservices based on UAT | Debug webservices based on UAT | Debug web services | Coding for web service bid status
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 13
Person | Question | Week: 11/11/2019 to 17/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Cliffen | What did you do yesterday? | Finish bid status web service | Non-working day | Integration, testing and debugging | Meeting to review progress and prepare for deployment | AWS Deployment | Meeting and regression testing | Debugging for web services
| What will you do today? | Non-working day | Integration, testing and debugging | Meeting to review progress and prepare for deployment | AWS Deployment | Meeting and regression testing | Debugging for web services | Final round of testing, debugging, final submission
| Do you have any obstacles? | No | No | No | No | No | No | No
Wen Rui | What did you do yesterday? | Non-working day | Finish UI code before integration | Testing web service after integration | Meeting 10 to review progress | AWS deployment | Meeting to prepare for submission, testing and debugging | Debugging for UI
| What will you work on today? | Finish UI code before integration | Testing web service after integration | Meeting 10 to review progress | AWS deployment | Meeting to prepare for submission, testing and debugging | Debugging for UI | Final round of testing, debugging, final submission
| Do you have any obstacles? | No | No | No | No | No | No | No
Yi Fan | What did you do yesterday? | Non-working day | Remaining UI coding before integration | Manual and Json Testing | Meeting to check testing and debugging progress | Deploy to AWS | Meeting for project submission preparation and testing | Debug UI problems
| What will you work on today? | Remaining UI coding before integration | Manual and Json Testing | Meeting to check testing and debugging progress | Deploy to AWS | Meeting for project submission preparation and testing | Debug UI problems | Final round of testing, debugging, final submission
| Do you have any obstacles? | No | No | No | No | No | No | No
Xian Shuang | What did you do yesterday? | Code bid status web service | Non-working day | Integration and testing | Meeting 10 for progress review | Deploy to AWS | Meeting 11, testing of deployed app (regression) | Json debugging
| What will you work on today? | Non-working day | Integration and testing | Meeting 10 for progress review | Deploy to AWS | Meeting 11, testing of deployed app (regression) | Json debugging | Final round of testing, debugging, final submission
| Do you have any obstacles? | No | No | No | No | No | No | No

## Week 14
Person | Question | Week: 18/11/2019 to 24/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Cliffen | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Wen Rui | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Yi Fan | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Xian Shuang | What did you do yesterday?
What will you work on today?
Do you have any obstacles?