## Slide 1: Group 7 PM Review Cliffen, Wen Rui, Yi Fan, Xian Shuang

## Slide 2: Functionalities
Do you plan to drop/add any functionalities?
  No plans to drop functionalities
  Additional functionalities
    Display student’s current timetable
    Search for classes via class names
Do you plan to use any PHP frameworks?
  No

## Slide 3: Functionalities
Did you manage to finish login + 1 functionality? Yes.
  What functionalities have you finished?
    User and Admin login
    Admin authentication and bootstrap
What is the IP address and admin password for your cloud deployment?
  3.1.203.13
  User: admin
  Password: 123

## Slide 4
Schedule

## Slide 5: Critical path Critical path
1
Schedule planning
0
1
1
1
1
3
Bootstrap without validation
2
4
4
2
2
Admin login page
1
2
3
4
3
2
User login page
7
2
3
9
4
Bootstrap with validation
0
5
8
8
5
2
Manual testing
1
10
1
Test bootstrap & bug log
0
1
Debugging
0
2
Preparation of slides
0
15
15
14
14
13
13
13
13
12
12
12
12
3
Create JSON checker
0
11
11
9
9
12
11
11
10
0
1
Create test cases for manual testing
1
10
10
9
9
18/9
19/9
19/9
19/9
19/9
22/9
26/9
26/9
29/9
27/9
30/9
1/10
1
Create bug metrics
9
11
2
2
11
Iteration 1
Notes: Scheduling planning [1]
Preparation of slides []
Create test cases []
Create bug metrics [2]
Admin Login page [2]
Bootstrap (1. Without validation 2. With validation) [2] [3]
Code json checker [3]
Test bootstrap using json checker & bug log [4]
Manual testing []
User login page [3]
Create simple test cases [2]

## Slide 6: cal path
2
Admin dump/start/ stop functions
1
2
3
2
1
Create JSON & manual test cases
2
1
1
3
3
2
Testing & Debugging
0
4
5
5
4
1
AWS database deployment
0
2
Admin round1 clearing logic
0
2
Testing & debugging
0
10
10
9
9
8
7
8
7
11
11
11
11
1
1
Create JSON/Manual test cases
2
1
User bidding functions
0
6
6
6
6
8
8
6
6
03/10
03/10
03/10
06/10
08/10
08/10
3
Bootstrap validations & JSON validations
0
3
3
1
1
1
Slides preparation
0
13
13
13
13
15/10
1
Testing & debugging
0
12
12
12
12
14/10
9/10
13/10
11/10
Iteration 2
Notes: Scheduling planning [1]
Preparation of slides []
Create test cases []
Create bug metrics [2]
Admin Login page [2]
Bootstrap (1. Without validation 2. With validation) [2] [3]
Code json checker [3]
Test bootstrap using json checker & bug log [4]
Manual testing []
User login page [3]
Create simple test cases [2]

## Slide 7: al path l path C al path
2
Code Admin Rd 2 Clearing Logic
0
1
2
2
1
2
Testing & Debugging
0
3
4
4
3
2
Testing & Debugging
0
1
Code admin dump (user & bid & section) functions
0
1
Deploy database to AWS
0
10
10
10
10
8
9
9
8
7
6
7
6
1
Code admin update bid & drop section functions
0
5
5
5
5
1
Create JSON & Manual test cases
0
5
5
5
5
17/10
17/10
19/10
21/10
21/10
24/10
1
Create JSON Test cases
1
2
1
1
2
1
Create JSON & Manual test cases
0
8
8
8
8
24/10
1
Testing & Debugging
0
9
9
9
9
3
Testing & Debugging
0
13
11
13
11
27/10
22/10
25/10
26/10
Iteration 3
Notes: Scheduling planning [1]
Preparation of slides []
Create test cases []
Create bug metrics [2]
Admin Login page [2]
Bootstrap (1. Without validation 2. With validation) [2] [3]
Code json checker [3]
Test bootstrap using json checker & bug log [4]
Manual testing []
User login page [3]
Create simple test cases [2]

## Slide 8
2
Code to fix problems from UAT
0
1
2
2
1
2
Testing & Debugging
0
8
7
8
7
2
Code additional features (improve search function)
1
5
5
4
4
10/11
31/10
03/11
06/11
1
Testing & Debugging
0
3
3
3
3
02/11
3
Code additional features (student timetable)
0
6
6
4
4
03/11
1
Code CSS for user interface
0
9
9
9
9
08/11
1
Deploy database to AWS
0
10
10
10
10
3
Testing & Debugging
0
13
11
13
11
09/11
Iteration 4
Notes: Scheduling planning [1]
Preparation of slides []
Create test cases []
Create bug metrics [2]
Admin Login page [2]
Bootstrap (1. Without validation 2. With validation) [2] [3]
Code json checker [3]
Test bootstrap using json checker & bug log [4]
Manual testing []
User login page [3]
Create simple test cases [2]

## Slide 9
1
Code additional features
0
1
1
1
1
2
Testing & Debugging
0
3
2
3
2
1
Submission of final project documents
0
4
4
4
4
14/11
15/11
17/11
3
Prepare for final presentation
0
7
5
7
5
18/11
Iteration 5
Notes: Scheduling planning [1]
Preparation of slides []
Create test cases []
Create bug metrics [2]
Admin Login page [2]
Bootstrap (1. Without validation 2. With validation) [2] [3]
Code json checker [3]
Test bootstrap using json checker & bug log [4]
Manual testing []
User login page [3]
Create simple test cases [2]

## Slide 10: Bug Metrics
What is the current value for the metric & did you have to take any action according to your mitigation plan?

## Slide 11: Roles & Responsibilities
Who is doing what (Project Manager, coder, etc.)?
What is the rotation plan? List specifically the PM is in charge of which milestone?